## Sheet1
Project Team
1 | UNSW Linker |  |  | Poject Manager | Principle Developer | Principle Engineer | Testing Engineer | Project Administrator | Contract Administrator | Trainer
| 1.1 | Project Management
|  | 1.1.1 | Stage Goals | A | I | I | I | R
|  | 1.1.2 | Communication | A | I | I | I | R
|  | 1.1.3 | Risk control | A |  |  |  | R
|  | 1.1.4 | Plan management | A | I | I | I | R
| 1.2 | Development
|  | 1.2.1 | Client-side | A | R | I | I
|  | 1.2.2 | Server-side | A | R | I | I
|  | 1.2.3 | Website | A | R | I | I
|  | 1.2.4 | UNSW SSO system | A | R | I | I
| 1.3 | Design&Interface
|  | 1.3.1 | Server-side design | A | I | R | I
|  | 1.3.2 | Website design | A | I | R | I
|  | 1.3.3 | Interface | A | R |  | I
| 1.4 | Test
|  | 1.4.1 | Modular test | A | I | I | R
|  | 1.4.2 | Client-side test | A | I | I | R
|  | 1.4.3 | Servver-side test | A | I | I | R
|  | 1.4.4 | UI/UX test | A | I | I | R
|  | 1.4.5 | Public test | A | I | I | R
| 1.5 | Publication
|  | 1.5.1 | Dmo demonstration | A | C |  | R
|  | 1.5.2 | Maintain staff training | A | C |  |  |  |  | R
|  | 1.5.3 | Student guideline | A | C |  |  |  |  | R
|  | 1.5.4 | Feedback&Maintain | A | C |  |  |  |  | R
| 1.6 | Human Resouce
|  | 1.6.1 | Recruitment | A |  |  |  | R | C
|  | 1.6.2 | Finance | A |  |  |  | R | C

## Sheet4
Project Team
1 | UNSW Linker |  |  | Poject Manager | Principle Developer | Principle Engineer | Testing Engineer | Trainer | Intern
| 1.1 | Project Management
|  | 1.1.1 | Stage Goals | AR | I | I | I |  | I
|  | 1.1.2 | Communication | AR | I | I | I |  | I
|  | 1.1.3 | Risk control | AR
|  | 1.1.4 | Plan management | AR | I | I | I |  | I
| 1.2 | Development
|  | 1.2.1 | Client-side | A | R | I | I
|  | 1.2.2 | Server-side | A | R | I | I
|  | 1.2.3 | Website | A | R | I | I
|  | 1.2.4 | UNSW SSO system | A | R | I | I
| 1.3 | Design&Interface
|  | 1.3.1 | Server-side design | A | I | R | I
|  | 1.3.2 | Website design | A | I | R | I
|  | 1.3.3 | Interface | A | R |  | I
| 1.4 | Test
|  | 1.4.1 | Modular test | A | I | I | R
|  | 1.4.2 | Client-side test | A | I | I | R
|  | 1.4.3 | Servver-side test | A | I | I | R
|  | 1.4.4 | UI/UX test | A | I | I | R
|  | 1.4.5 | Public test | A | I | I | R
| 1.5 | Publication
|  | 1.5.1 | Dmo demonstration | A | C |  |  | R
|  | 1.5.2 | Maintain staff training | A | C |  |  | R
|  | 1.5.3 | Student guideline | A | C |  |  | R
|  | 1.5.4 | Feedback&Maintain | A | C |  |  | R
| 1.6 | Human Resouce
|  | 1.6.1 | Recruitment | AC |  |  |  |  | R
|  | 1.6.2 | Finance | ARC

## Sheet2
Stakeholder | Unaware | Resistant | Neutral | Supportive | Leading | Stakeholder | Category | Interest(0-3) | Influence(0-3) | Expectations | Communication Channel
UNSW management |  |  |  | CD |  | UNSW management | Primary | 3 | 3
Project management Team |  |  |  | C | D | Project management Team
design engineers,developer |  |  | C |  | D | design engineers,developer
students | C |  |  | D |  | students
staffs | C |  |  | D |  | staffs
other school | C |  | D |  |  | other school
suppliers | C |  | D |  |  | suppliers

## Sheet3
Stakeholder | Category | Interest(0-3) | Influence(0-3) | Roles | Communication Channel
UNSW management | Primary | 3 | 3 | Fully function and demand of UNSW online platform. | Phone call updates for high level milestones. Weekly Teams meeting.
Project management Team | Secondary | 2 | 3 | Project life cycle management, including requirements, plans, progress, quality, risk and cost management. | daily Teams meeting.
design engineers,developer | Secondary | 1 | 3 | Complete the project | daily Teams meeting.
students | Secondary | 2 | 2 | A group of indirect stakeholders who gain a better experience with the online platform. | Feedback forms
staffs | Secondary | 2 | 2 | A group of indirect stakeholders who gain a better experience with the online platform. | Feedback forms
suppliers | Tertiary | 1 | 1 | on time payments for the equipment | contract negotiations, Phone calls for urgent communications
other school | Teritary | 1 | 1 | Provide references and opinions for the platform | email

## Sheet5
Project Team
1 | UNSW Linker |  |  | Poject Manager | Principle Developer | Principle Engineer | Testing Engineer | Trainer | O&M | HR
| 1.1 | Project Management
|  | 1.1.1 | Stage Goals | AR | I | I | I |  | I | I
|  | 1.1.2 | Communication | AR | I | I | I |  | I | I
|  | 1.1.3 | Risk control | AR | [5 empty] | I
|  | 1.1.4 | Plan management | AR | I | I | I |  |  | I
| 1.2 | Development
|  | 1.2.1 | Client-side | A | R | I | I |  | I
|  | 1.2.2 | Server-side | A | R | I | I |  | I
|  | 1.2.3 | Website | A | R | I | I |  | I
|  | 1.2.4 | UNSW SSO system | A | R | I | I |  | I
| 1.3 | Design&Interface
|  | 1.3.1 | Server-side design | A | I | R | I |  | I
|  | 1.3.2 | Website design | A | I | R | I |  | I
|  | 1.3.3 | Interface | A | R |  | I |  | I
| 1.4 | Test
|  | 1.4.1 | Modular test | A | I | I | R |  | I
|  | 1.4.2 | Client-side test | A | I | I | R |  | I
|  | 1.4.3 | Servver-side test | A | I | I | R |  | I
|  | 1.4.4 | UI/UX test | A | I | I | R |  | I
|  | 1.4.5 | Public test | A | I | I | R |  | I
| 1.5 | Publication
|  | 1.5.1 | Dmo demonstration | A | C |  |  | R
|  | 1.5.2 | Maintain staff training | A | C |  |  | R
|  | 1.5.3 | Student guideline | A | C |  |  | R
|  | 1.5.4 | Feedback&Maintain | A | C |  |  | R
| 1.6 | Human Resouce
|  | 1.6.1 | Recruitment | AC | [5 empty] | R
|  | 1.6.2 | Finance | ARC