## Sheet1
|  | Insufficient | Adequate | Good | Accomplished | Advanced |  | How to get to 100%
| Weighting | 0-50 | 50-65 | 65-75 | 75-85 | 85-100
Alignment with course content and reading materials | 10 | Clear signs that the authors have not applied the course content, for example confused terminology, errors in application of concepts, and/or significant parts missing | There are some basic descriptions of scope, schedule, budget and risk applied. However they may feel amateur and have likely been developed based on PM general knowledge. | All the parts of a project management plan required for the assignment are present and have been applied mostly correctly. | Appropriate use of PM tools, applied competently. References show the origin of the PM techniques being applied. | Skilled use of PM tools , which have been selected from a range of options to respond to the characteristics of this project. Supported by referencing. | 75 | 1. Use referencing to course material for PM tools across the plan (important - I actually asked for this) 2. Use more narrative to say why and how you are applying the PM methods, e.g. what was appropriate? What did you miss out? Why? 3. Use punchy prose in the HR plan. Use the communication plan to deliver actual strategic outcomes (not just to faciliate the work). Fix the shortcomings in the risk mgmt plan - see comments in pdf doc. Consider some opportunites as well.
Exercise of reasonable judgement and careful use of assumption | 10 | Weird decisions, elephants in the room, serious lack of detail and/or use of sweeping assumptions to make problems go away | The plan is reasonable but may have some gaps which leave doubts that it can be delivered in the real world. | The project plan seems sensible. There is an awareness of uncertainty and planned responses to this uncertainty. | The project plan provides confidence that it can succeed. Assumption and risk clearly linked. Evidence of effort to identify and analyse possible future events, and build responses to these into the project plan. | The project has been structured in a strategic way to deal with uncertainty. E.g. stage gates, iterative design methods and/or rolling wave planning. (Needs to have everything from the box on the left as well) | 80 | 3.Integrate the risk responses into the main plan (i.e. do the 'second pass' of the project plan). Make it clear which tasks in the schedule are primary WP tasks and which are contingency plans. Do the same for the budget. 4. It seems you have designated some parts as being managed iteratively, but this has not been developed in the plan. Make this more explicit, add a short paragraph in an appropriate place to explain why and how. 5. Provide more narrative to guide the reader through the plan. What does stuff mean? what is the implication of your decisions? How do the parts fits together?
Level of integration of the project plans | 5 | It is unclear how the different parts of the plan are related, may include self-contradictions | The different parts of the project management plan are probably compatible, but this has not been explicitly shown to be the case. | Evidence that appropriate steps have been followed in the development of the project management plan and project charter and the different parts are clearly related. | A systematic approach shows that all the parts of the project management plan can be related to one another. | End to end mapping from objectives, though scope, schedule, budget, risk and contingencies. No loose ends. | 85 | 6. Use a crossreferencing system to link together deliverables, risks, assumptions, contingencies, mitigations, WPs, budget items.
Project Charter presentation | 5 | Unclear why the project would be undertaken by this organisation. | The project seems to belong in this organisation but it is not clear what the reason(s) for this might be. | Shows clear links between the project objectives, deliverables, scope, and the strategic objectives of the organisation. | Everything from the box to the left, AND a clear skeleton of a plan to deliver the project, though may not be ready to ask for funding at this stage. | The project clearly matches organistational strategy and the content of the presentation provides confidence that this project will succeed in delivering the benefits. Let's do it right now!